## GanttChart
CareCore: Healthcare System ¦ Project Schedule
Egyptian Russian University (ERU)
| Project Start Date | 2024-10-01 |  |  |  | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18
| Project Lead | Sama El-Sayed | [5 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27
 | time axis 2024-09-30 to 2025-02-02
WBS | TASK | LEAD | PREDECESSOR | START | END | % DONE | WORK DAYS | time axis 2024-09-30 to 2025-02-02
1 | Project intiation | [5 empty] | 7
.1 | Identify key stakeholders | - |  | 2024-10-01 | 2024-10-02 | 100% | 1
.1 | Regulatory and compliance analysis | - |  | 2024-10-01 | 2024-10-03 | 100% | 2
1.2.1 | Research applicable regulations | - |  | 2024-10-01 | 2024-10-02 | 100% | 1
.1 | Project Charter Development | - |  | 2024-10-08 | 2024-10-09 | 100% | 1
.1 | Define Scope, objectives, High-level requirements and Budget | - |  | 2024-10-08 | 2024-10-09 | 100% | 1
.1 | Finalize Project Charter Approval from the stakeholders | - |  | 2024-10-08 | 2024-10-09 | 100% | 1
1 | Requirements Gathering | [5 empty] | 7
.1 | Conduct meetings with stakeholders | - |  | 2024-10-15 | 2024-10-17 | 100% | 2
2.1.1 | Determine functional and non-functional requirements | - |  | 2024-10-15 | 2024-10-16 | 100% | 1
.1 | System Architecture Design | - |  | 2024-10-22 | 2024-10-24 | 100% | 2
2.2.1 | Define technical architecture | - |  | 2024-10-22 | 2024-10-23 | 100% | 1
2.2.2 | Develop workflows | - |  | 2024-10-22 | 2024-10-23 | 100% | 1
1 | Patient Portal | [5 empty] | 14
.1 | Build profile management features | - |  | 2024-10-29 | 2024-10-31 | 100% | 2
3.1.1 | Develop appointment scheduling and history tracking | - |  | 2024-10-29 | 2024-10-30 | 100% | 1
3.1.2 | Implement secure chats with doctors | - |  | 2024-11-05 | 2024-11-06 | 100% | 1
.1 | Doctor Dashboard | - |  | 2024-11-05 | 2024-11-06 | 100% | 1
3.2.1 | Create patient consultation tools | - |  | 2024-11-05 | 2024-11-06 | 100% | 1
3.2.2 | Integrate treatment history and notes | - |  | 2024-11-12 | 2024-11-13 | 100% | 1
3.3 | Hospital Admin Panel | - |  | 2024-11-12 | 2024-11-13 | 100% | 1
3.3.1 | Build contract management module | - |  | 2024-11-12 | 2024-11-13 | 100% | 1
3.3.2 | Develop performance tracking and reporting tools | - |  | 2024-11-19 | 2024-11-20 | 100% | 1
3.4 | System Integration | - |  | 2024-11-19 | 2024-11-21 | 100% | 2
3.4.1 | EHR Integration | - |  | 2024-11-19 | 2024-11-20 | 100% | 1
3.4.2 | Payment Integration | - |  | 2024-11-26 | 2024-11-27 | 100% | 0.5
1 | Database Intiation | [5 empty] | 7
.1 | Design database schema | - |  | 2024-11-26 | 2024-11-28 | 100% | 2
4.1.1 | Implement data encryption and access controls | - |  | 2024-11-26 | 2024-11-27 | 100% | 1
.1 | Date Migration | - |  | 2024-12-03 | 2024-12-04 | 100% | 1
.1 | Analytics and Reporting | - |  | 2024-12-03 | 2024-12-04 | 100% | 1
4.3.1 | Develop user analytics dashboard | - |  | 2024-12-03 | 2024-12-04 | 100% | 1
4.3.2 | Create regulatory compliance reports | - |  | 2024-12-03 | 2024-12-04 | 100% | 1
1 | Identify test scenarios and cases | [5 empty] | 7
.1 | Develop a test schedule | - |  | 2024-12-10 | 2024-12-13 | 100% | 3
5.2 | Functional Testing | - |  | 2024-12-10 | 2024-12-12 | 100% | 2
5.2.1 | Test individual modules | - |  | 2024-12-10 | 2024-12-11 | 100% | 1
5.3 | Security and Performance Testing | - |  | 2024-12-17 | 2024-12-18 | 100% | 1
1 | Deployment Planning | [5 empty] | 8
.1 | Go-Live Planning Checklist | - |  | 2024-12-17 | 2024-12-18 | 100% | 1
6.1.1 | Generate a rollback procedure | - |  | 2024-12-17 | 2024-12-18 | 100% | 1
6.2 | Pilot program | - |  | 2024-12-24 | 2024-12-25 | 100% | 1
6.2.1 | Deploy in a selected hospital network | - |  | 2024-12-24 | 2024-12-25 | 100% | 1
6.2.2 | Collect feedback and address issues | - |  | 2024-12-24 | 2024-12-25 | 100% | 1
6.3 | Full System Deployment | - |  | 2024-12-31 | 2025-01-01 | 0% | 1
6.3.1 | Implement system across all contracted hospitals | - |  | 2024-12-31 | 2025-01-01 | 0% | 1
6.3.2 | Monitor initial performance | - |  | 2024-12-31 | 2025-01-01 | 0% | 1
1 | User Training | [5 empty] | 13
.1 | Integration and usability testing | - |  | 2025-01-07 | 2024-01-12 | 0% | 5
7.1.1 | End-to-End testing | - |  | 2025-01-07 | 2024-01-11 | 0% | 4
7.2 | User Acceptance Testing (UAT) | - |  | 2025-01-07 | 2024-01-11 | 0% | 4
1 | System Monitoring and Maintanence | [5 empty] | 5
.1 | Set up performance monitoring tools | - |  | 2025-01-14 | 2025-01-17 | 0% | 3
8.2 | Collect user feedback through surveys | - |  | 2025-01-14 | 2025-01-16 | 0% | 2
1 | Enhancements | [5 empty] | 4
.1 | AI-Powered Enhancements | - |  | 2025-01-21 | 2025-01-23 | 0% | 2
9.1.1 | AI chatbots for scheduling and support | - |  | 2025-01-21 | 2025-01-23 | 0% | 2